## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Siva Sai D | 2026-02-10 | Product images failing to load due to piped multiple URL strings in the database | Milestone 2 (Weeks 3-4) | Self | Logical | Implemented string parsing logic to extract the first valid URL from the piped string | 2026-02-12 | Closed | UI now successfully renders primary product thumbnails
2 | Siva Sai D | 2026-02-24 | SettingWithCopyWarning thrown during Pandas user-item matrix generation, causing state instability | Milestone 3 (Weeks 5-6) | Self | Backend | Refactored dataframe manipulation using .loc to ensure safe data mutation | 2026-02-25 | Closed | Data pipeline runtime optimized and warnings resolved
3 | Siva Sai D | 2026-03-05 | Razorpay SDK integration fails to initialize, blocking the checkout flow | Milestone 3 (Weeks 5-6) | Self | Integration | Replaced broken SDK call with a reliable link-based payment redirect | 2026-03-08 | Closed | Payment flow fully functional with correct order totals
4 | Siva Sai D | 2026-03-15 | AI Chatbot outputs raw numeric prices instead of properly formatted Rupee currency | Milestone 4 (Weeks 7-8) | Self | UI/UX | Updated chatbot system prompt and frontend logic to enforce standard currency formatting | 2026-03-16 | Closed | Chatbot now accurately reflects localized currency (₹)
5 | Siva Sai D | 2026-03-20 | Star ratings on product detail pages show excessive trailing decimals (e.g., 4.333333) | Milestone 4 (Weeks 7-8) | Self | UI/UX | Added formatting logic in Reflex state to round star ratings to one decimal place | 2026-03-20 | Closed | Enhanced visual consistency across product grids

## Sheet2
Logical
User Interface
Maintainability
Standards
Others